## Sheet1
______@___Architects.com 555-555-5555 P.O. Box 555 Your City, Your State Yourzip, YourCompany Name
Your State license number(s)
| PROJECT: | Project Name
| ACTIVITY: | Architectural Construction Administration SITE VISIT: CA-SV- | [8 empty] | 1
| VISIT DATE: | date of site visit
CA-SV™ form
© Copyright 2015 ArCH: Architects Creating Homes, LLC All Rights Reserved Worldwide.
PURPOSE |  | WEATHER | [7 empty] | ON-SITE ACTIVITIES IN GENERAL
|  | Sun |  |  |  | Humidity | Wind
To verify GC latest Pay Request. |  | sunny |  |  |  | damp | windy |  |  | Forms for foundation walls completely stripped and
|  | partly cloudy |  |  |  | wet | still |  |  | stacked on truck. GC cleaning site and crawlspace.
|  | cloudy |  |  |  | misty | light breeze
rain
|  | Visibility |  |  |  | dry | Temp | 61 | *F | CONDITIONS IN GENERAL
|  | clear |  |  |  | snow |  |  |  | Site dry, some stored non-organic soil stored in pile
|  | hazy |  |  |  | ice |  |  |  | on-site.
PHOTOS TAKEN DURING SITE VISIT | [5 empty] | LIST OF ITEMS REQUIRING ADJUSTMENT
|  |  | 1 | . | 1 | ORGANIC EXISTING ROOTS/SOIL
There appears to be about 18”+/- of original virgin organic topsoil with lots of roots at
the original mountain slope inside the garage. Do NOT place fill on top of this. Instead:
per the Geotechnical Report, remove all organic topsoil, roots and related debris from
any area where structure (including the garage slab) will be placed above it.
GC: please have Geotech Engineer observe filling and compaction procedures.
INSTRUCTIONS:
The above is an example CA-SV Report item and where things are supposed to be
located in the report.
Use Excel's features to insert graphic arrows, like the one to the left. Recommend
that you use a white arrow with black outline, which will work on any kind of background.
Use Excel to insert and remove rows. Suggest that you NOT remove or alter columns,
as this could damage this layout.
Use Excel's "FILL JUSTIFY" command/tool to arrange text in each paragraph. While this
isn't as convenient as MS Word's text handling capabilities, the Excel forrmat of rows
and columns is easier to handle for the insertion of photos and numbered paragraphs
that are partially automated and general organization of a CA Report.
Use Excel's insert feature to insert JPG digital photos of your CA-SV.
You can also use Excel's highlight feature to emphasize something like this:
See Sheet A3.1 for plans.
It is highly recommended that you "print" your reports as a PDF, then email those
to your project team members (Client, GC, Engineers), so that no one can alter
your original report.
|  |  | 1 | . | 2 | NEXT ITEM
|  |  | 1 | . | 3 | NEXT ITEM
|  |  | 1 | . | 4 | NEXT ITEM
|  |  | 1 | . | 5 | NEXT ITEM
LOOKING AHEAD NEAR TERM ITEMS
|  |  | 1 | . | 6 | NEXT ITEM
|  |  | 1 | . | 7 | NEXT ITEM
|  |  | 1 | . | 8 | NEXT ITEM
|  |  | 1 | . | 9 | NEXT ITEM
GENERAL COMMENTS
|  |  | 1 | . | 10 | NEXT ITEM
|  |  | 1 | . | 11 | NEXT ITEM
|  |  | 1 | . | 12 | NEXT ITEM
|  |  | 1 | . | 13 | NEXT ITEM
|  |  | 1 | . | 14 | NEXT ITEM
|  |  | 1 | . | 15 | NEXT ITEM
|  |  | 1 | . | 16 | NEXT ITEM
|  |  | 1 | . | 17 | NEXT ITEM
|  |  | 1 | . | 18 | NEXT ITEM
|  |  | 1 | . | 19 | NEXT ITEM
|  |  | 1 | . | 20 | NEXT ITEM
|  |  | 1 | . | 21 | NEXT ITEM
|  |  | 1 | . | 22 | NEXT ITEM
|  |  | 1 | . | 23 | NEXT ITEM
This concludes Construction Site Visit |  | 1 |  |  |  | please contact Architect for more information/questions
insert your company logo in this general area