## Sheet1
00320 BASE BID PRICING QUOTATION (BID) FORM
This is Page 1 of a 2 spreadsheet page form.
Page 2 is reached by clicking on the "Sheet 2" tab at the bottom of this window. This Page 1 can be returned to by
clicking on the Page 1 tab, if you are on Sheet 2 and wish to return to this sheet.
Page 2 is the actual spreadsheet where the Base Bid Line Items prices will be listed by you.
The Page 1 is what turns that Page 2 sheet into a BASE BID PRICING QUOTATION FORM.
After Bid Date, no longer use this Page 1, as the Page 2 spreadsheet will then become a spreadsheet for other uses.
See Instructions on the Page 2 spreadsheet.
Please keep these Sheets arranged as they are. SEND this Excel file back to the Architect on Bid Day, please, with all blanks
filled out. You do not need to printout hardcopy. Transmission of this electronic file filled out and emailed back to the Architect,
along with the other spreadsheet electronic files the Architect has emailed you is all that is required.
Fill in legibly, on your computer, with at least 10point Arial font, using exactly this form, with No modifications other than the
insertion of your prices & your company name and other requested information, please.
PROJECT : |  | (architect type project title here) |  |  |  | (Architect
|  | (a new residence for Bob & Barbara Smith), |  |  |  | fills out
project
located at: |  | (street address) |  |  |  | information
|  | (City/Town) |  |  |  | to the left
|  | County (County), (state), (zip) |  |  |  | in tan)
Geographic Coordinates (latitude and longitude) :
|  | 32.86505* N, -80.00092* W | 5,659'+/- ASL
I, |  |  |  |  | , | (GC fills
|  | (GC representative enter your personal legal name in the box above) |  |  |  | out
information
duly authorized representative of : | [5 empty] | in light
gray to
| (enter GC company name in the box above) |  |  |  |  | the left)
(Company Physical Address):
(Company Mailing Address):
Office Phone:
Cell Phone:
Other Phone:
E-mail 1:
E-mail 2:
Website address:
do hereby provide this Base Bid Pricing bid for the above indicated Project, as indicated in the Architect and Engineer's
documents.
Architect: |  | (architect company name by trademark)
(legal name of firm)
|  |  | # | dated | (List numbers: 1,2,3,4, etc,
We acknowledge receipt of Addenda: |  |  | 1 |  | and the dates of each in the
|  |  | 2 |  | blanks to the left)
provided to us by the Architect. |  |  | 3 |  | (Dates indicate receipt)
4
5
6
7
8
Structural Engineer: |  | XYZ Structural Engineers, LLC
Architectural Project document date: (for title sheet): |  |  | / /2015
Structural Engineer's Project document date: |  |  | / /2015
Our bid is the price for which we are agreeing to provide and construct this Project. However, this bid form is Not a
contract and does not bind us to do anything, other than indicating our intent to possibly agree to sign a contract to build
this project, at some point in the future, although we have no binding requirement to do that at this point. Our bid and the
documents upon which we base it will become the basis for our Contract with the Owner. Our bid price is the amount of
money we will expect to be paid to build the Project's Base Bid features, including all costs, overhead & profit (OH & P),
insurance and all other costs associated with our building this Project in accordance with the Architect & Engineer's
documents and the attached Bid Forms. We are agreeing that in providing this Bid, we and our suppliers, subcontractors
and employees involved with this Project have thoroughly reviewed the Project documents and understand all of the
Drawings, Specifications, and other documents associated with this Project.
(The General Contractor will fill in his/her pricing in the blanks in the Bid Form on Sheet2 below):
STAFFING APPROACH: it is requested that the GC fill out the following blanks of their staffing approach to this
project. Some of these roles may be shared; that is entirely up to the Contractor; we would simply like to
understand the intentions.
Lead person on-site most frequently working & managing project in the field:
Estimated # hours per week this person would be on the job on site:
Administrative person in office coordinating orders & staffing:
Person checking job for Quality Control :
END OF SHEET 1. SEE SHEET 2 ON TAB BELOW FOR THE ACTUAL SPREADSHEET FORM

## Sheet2
4 in 1
BASE BID FORM VALUE ENGINEERING SCHEDULE of VALUES PAY REQUEST
during Bidding during Negotiations during Lending approval process during Construction
Owner-Borrower(s): |  | Owner name here |  |  | Pay Request #: |  |  |  | 1 |  | 0 | <--TOTAL BANK DRAW THIS INVOICE
Property: |  | Property address here |  |  | Date of this Pay Request: |  |  |  | 2015-04-27
Contractor: |  | Contractor name here |  |  | Amount now due & payable to Contractor: |  |  |  | 0 |  |  |  |  | This form has been coordinated with other ArCHforms, including ArCHspec™
Bank/Lender: |  | Lender name here (if any) |  |  | Sent to: | Architect company name here | [7 empty] | 4 in 1 ™ ArCHform 2015.1
© Copyright 2015, ArCH: Architects Creating Homes, All Rights Reserved Worldwide.
Instructions: | Note: this is Sheet 2 of a 2 sheet spreadsheet file.
Sheet 1 is the first sheet that makes this sheet 2 into a BID FORM. Please fill out Sheet 1 first, then fill out this Sheet 2.
Email this entire multiple-page spreadsheet back to the Architect on Bid Date and Time as it is presently formatted. Only fill in blanks indicated. Thank you.
1. GC (General Contractors) use this form as their Bid Form 1st. Architect may prefer to populate the Items To Be Completed column with other items, which is optional, of Architect's choosing.
2. 2nd: GC use this form next during Negotiations for Value Engineering. 3rd: GC use this form as the Schedule of Values for Owner's Lender. 4th: GC use this form as GC Pay Requests during Construction.
3. There are several blank line items in the column below under Items To Be Completed, which the GC may use to insert project-specific items not normally appearing in this list. Also: GC and Architect may insert additional rows to provide more custom line items, if necessary.
4. When Lenders have institution-specific list of Items To Be Completed on their own Schedule of Values form (that they may insist on using) that may vary from those on this form, ask GC to modify the Items To Be Completed list with the Lender's Items, or Architect adjust to suit.
GC to provide his Budget amounts for each Item in the Light Tan column. Once that is done, and the Lender is in agreement, this column of numbers should remain fixed and not altered.
5. When it comes time for the GC to begin making Pay Requests, GC to USE THIS FORM AS their Pay Request form. This Bid Form/Schedule of Values form becomes the Pay Request form.
6. From that point on, GC to only revise the percentages in BLUE (in the Light Gray column), and starting with the 2nd Pay Request, the BLUE cash values (in the Light Green column) to record Previous amounts billed to date. All of the Red formulas are on auto-pilot and should Not be changed.
7. Change Orders will Not likely be considered by any Lender, once the loan amount is fixed. Change Orders should be processed separately by the Owner, GC and Architect, separate from this form, unless Owner is a Governmental entity.
8. In instances where Owner is providing certain materials paid for separately by the Owner, and GC is installing, insert GC installation charges for those line items below. Below does Not include the Owner's separate material costs for such items. This spreadsheet should only include GC charges.
9. Not necessarily all of the Line Items below apply to this project. Ignore & leave blank those that do not apply. If there are several new Line Items that should be there, but are Not, Architect may insert those new Line Items in the appropriate Division.
|  |  | GC enter Quotes during Bidding, then leave fixed. If numbers are already here, replace them |  |  |  | Revise for each Pay Request |  | Starting with 2nd Pay Request, revise for each Pay Request
[5 empty] | Do NOT adjust any items in RED | [5 empty] | Do NOT adjust any items in RED |  | Contractor enter any explanatory notes desired
[7 empty] | % | Amount | Previous | Amount Due | Amount | % Remaining
|  |  | Quote/ | GC | Subtotal | Line Item | Complete | Earned | Amount Billed | This Pay | Remaining | To Complete | Contractor notes
LINE ITEMS TO BE COMPLETED |  |  | Budget | Profit | with Profit | % of Job | To Date | To Date | To Date | Request | To Complete | This Item
DIVISION 1 GENERAL CONDITIONS
Permits, Impact Fees, Insurance, Surveys, Site Safety |  |  | 1500 | 150 | 1650 | 0.3616% | 0% | 0 | 0 | 0 | 1650 | 100%
Blueprints, mailing, Submittals, Closeout Manuals, misc. OH |  |  | 800 | 80 | 880 | 0.1928% | 0% | 0 | 0 | 0 | 880 | 100%
GC Supervision/Coordination on site and off site |  |  | 25000 | 2500 | 27500 | 6.026% | 0% | 0 | 0 | 0 | 27500 | 100%
DIVISION 2 SITEWORK
Site Work, Clearing, Grading |  |  | 5000 | 500 | 5500 | 1.205% | 0% | 0 | 0 | 0 | 5500 | 100%
Termite & Ant Control Treatment |  |  | 600 | 60 | 660 | 0.1446% | 0% | 0 | 0 | 0 | 660 | 100%
Septic Tank, Sewer (to include all fees) |  |  | 4500 | 450 | 4950 | 1.085% | 0% | 0 | 0 | 0 | 4950 | 100%
Water Service Entance & Meter, Well |  |  | 1200 | 120 | 1320 | 0.2892% | 0% | 0 | 0 | 0 | 1320 | 100%
Electric Service Entrance |  |  | 2000 | 200 | 2200 | 0.4821% | 0% | 0 | 0 | 0 | 2200 | 100%
Driveway(s) |  |  | 7000 | 700 | 7700 | 1.687% | 0% | 0 | 0 | 0 | 7700 | 100%
Walkway(s) |  |  | 2000 | 200 | 2200 | 0.4821% | 0% | 0 | 0 | 0 | 2200 | 100%
Exterior slabs (not part of main building) |  |  | 800 | 80 | 880 | 0.1928% | 0% | 0 | 0 | 0 | 880 | 100%
Subterranean Drainage Piping connected to Down spouts |  |  | 800 | 80 | 880 | 0.1928% | 0% | 0 | 0 | 0 | 880 | 100%
Crawlspace drainage piping |  |  | 500 | 50 | 550 | 0.1205% | 0% | 0 | 0 | 0 | 550 | 100%
Misc. Site Drainage Piping |  |  | 800 | 80 | 880 | 0.1928% | 0% | 0 | 0 | 0 | 880 | 100%
Finish Grading |  |  | 2000 | 200 | 2200 | 0.4821% | 0% | 0 | 0 | 0 | 2200 | 100%
Debris & Site Clean up, Porta Toilets |  |  | 1400 | 140 | 1540 | 0.3375% | 0% | 0 | 0 | 0 | 1540 | 100%
Landscaping, site walls, exterior ornamental Items |  |  | 5000 | 500 | 5500 | 1.205% | 0% | 0 | 0 | 0 | 5500 | 100%
Exterior steps (such as stone, not covered in other Divisions) |  |  | 400 | 40 | 440 | 0.09642% | 0% | 0 | 0 | 0 | 440 | 100%
Fencing |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | #DIV/0!
Site signage (if any) |  |  | 120 | 12 | 132 | 0.02892% | 0% | 0 | 0 | 0 | 132 | 100%
DIVISION 3 CONCRETE
Footings, Foundations, Slabs (building-house) |  |  | 20000 | 2000 | 22000 | 4.821% | 0% | 0 | 0 | 0 | 22000 | 100%
Curbs and site surface guttering |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | #DIV/0!
Precast concrete (lintels, prestressed structural slabs) |  |  | 1200 | 120 | 1320 | 0.2892% | 0% | 0 | 0 | 0 | 1320 | 100%
DIVISION 4 MASONRY
Concrete Block work (CMU concrete masonry units) |  |  | 2800 | 280 | 3080 | 0.6749% | 0% | 0 | 0 | 0 | 3080 | 100%
Masonry Veneer: rock, brick, inside & out, & at fireplaces |  |  | 12000 | 1200 | 13200 | 2.892% | 0% | 0 | 0 | 0 | 13200 | 100%
DIVISION 5 METALS (structural)
Fittings, connectors, structural steel, & cold formed light gage |  |  | 1100 | 110 | 1210 | 0.2651% | 0% | 0 | 0 | 0 | 1210 | 100%
DIVISION 6 WOOD, FRAMING, CABINETRY, SIDING
Standard Framing: floors, walls, trusses, sheath, deck framing |  |  | 85000 | 8500 | 93500 | 20.49% | 0% | 0 | 0 | 0 | 93500 | 100%
Timber framing: large wood posts and beams |  |  | 12000 | 1200 | 13200 | 2.892% | 0% | 0 | 0 | 0 | 13200 | 100%
Fireplance: mantels |  |  | 700 | 70 | 770 | 0.1687% | 0% | 0 | 0 | 0 | 770 | 100%
Exterior Siding: Vinyl, Hardi- Board, wood |  |  | 10000 | 1000 | 11000 | 2.41% | 0% | 0 | 0 | 0 | 11000 | 100%
Exterior Trim: Soffit, Fascia |  |  | 3000 | 300 | 3300 | 0.7231% | 0% | 0 | 0 | 0 | 3300 | 100%
Exterior Porches, Decks (amounts not in framing) |  |  | 3500 | 350 | 3850 | 0.8436% | 0% | 0 | 0 | 0 | 3850 | 100%
Wood Ceilings |  |  | 6000 | 600 | 6600 | 1.446% | 0% | 0 | 0 | 0 | 6600 | 100%
Interior Trim |  |  | 2000 | 200 | 2200 | 0.4821% | 0% | 0 | 0 | 0 | 2200 | 100%
Attic access panels |  |  | 800 | 80 | 880 | 0.1928% | 0% | 0 | 0 | 0 | 880 | 100%
Stairs:Treads, Risers, Balusters & Railings |  |  | 14000 | 1400 | 15400 | 3.375% | 0% | 0 | 0 | 0 | 15400 | 100%
Flooring: Wood finish flooring |  |  | 6000 | 600 | 6600 | 1.446% | 0% | 0 | 0 | 0 | 6600 | 100%
Cabinets, Vanities (not including countertops) |  |  | 12000 | 1200 | 13200 | 2.892% | 0% | 0 | 0 | 0 | 13200 | 100%
Shelving (not in cabinetry above) |  |  | 1000 | 100 | 1100 | 0.241% | 0% | 0 | 0 | 0 | 1100 | 100%
Countertops |  |  | 4800 | 480 | 5280 | 1.157% | 0% | 0 | 0 | 0 | 5280 | 100%
DIVISION 7 THERMAL & MOISTURE PROOFING
Roof: Shingles, Metal, Tile, others |  |  | 12000 | 1200 | 13200 | 2.892% | 0% | 0 | 0 | 0 | 13200 | 100%
Flashing: at all locations: foundations, roof, walls, trim, etc. |  |  | 2500 | 250 | 2750 | 0.6026% | 0% | 0 | 0 | 0 | 2750 | 100%
Insulation: Wall, Roof-Attic, Floor, Crawl/Basement, Slab |  |  | 6500 | 650 | 7150 | 1.567% | 0% | 0 | 0 | 0 | 7150 | 100%
also: acoustical, air & water barriers.
Crawlspace Encapsulation, dehumidification |  |  | 2800 | 280 | 3080 | 0.6749% | 0% | 0 | 0 | 0 | 3080 | 100%
Gutters, Downspouts, gutter protection |  |  | 2800 | 280 | 3080 | 0.6749% | 0% | 0 | 0 | 0 | 3080 | 100%
Sealants & Caulking |  |  | 600 | 60 | 660 | 0.1446% | 0% | 0 | 0 | 0 | 660 | 100%
Foundation wall & cavity wall waterproof coatings & drainage |  |  | 1200 | 120 | 1320 | 0.2892% | 0% | 0 | 0 | 0 | 1320 | 100%
DIVISION 8 DOORS & WINDOWS
Exterior Doors & Windows (passage) |  |  | 45000 | 4500 | 49500 | 10.85% | 0% | 0 | 0 | 0 | 49500 | 100%
Garage Doors(s) (vehicular) |  |  | 6000 | 600 | 6600 | 1.446% | 0% | 0 | 0 | 0 | 6600 | 100%
Interior Doors |  |  | 4000 | 400 | 4400 | 0.9642% | 0% | 0 | 0 | 0 | 4400 | 100%
Door Hardware |  |  | 800 | 80 | 880 | 0.1928% | 0% | 0 | 0 | 0 | 880 | 100%
Shower enclosures (glass) with shower doors |  |  | 1200 | 120 | 1320 | 0.2892% | 0% | 0 | 0 | 0 | 1320 | 100%
DIVISION 9 FINISHES
Exterior Siding : Stucco |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | #DIV/0!
Sheetrock: (gypsum board) Hang, Finish |  |  | 8000 | 800 | 8800 | 1.928% | 0% | 0 | 0 | 0 | 8800 | 100%
Exterior Paint & Stain: Prime, Paint |  |  | 4500 | 450 | 4950 | 1.085% | 0% | 0 | 0 | 0 | 4950 | 100%
Interior Paint & Stain: Prime, Finish |  |  | 3500 | 350 | 3850 | 0.8436% | 0% | 0 | 0 | 0 | 3850 | 100%
Wall Tile: Kitchen Backsplash, Bathroom Walls |  |  | 2800 | 280 | 3080 | 0.6749% | 0% | 0 | 0 | 0 | 3080 | 100%
Flooring: Carpet (material & install) |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | #DIV/0!
Flooring: Tile (material & install) |  |  | 3500 | 350 | 3850 | 0.8436% | 0% | 0 | 0 | 0 | 3850 | 100%
DIVISION 10 SPECIALTIES
Louvers & Vents |  |  | 800 | 80 | 880 | 0.1928% | 0% | 0 | 0 | 0 | 880 | 100%
Fire Extinguishers (if any provided by GC) |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | #DIV/0!
Toilet Accessories: mirrors, med cab, ttd, towel bars, shwr rds |  |  | 400 | 40 | 440 | 0.09642% | 0% | 0 | 0 | 0 | 440 | 100%
Fireplaces: Insert (s) & related exhaust flue, cap & parts |  |  | 4800 | 480 | 5280 | 1.157% | 0% | 0 | 0 | 0 | 5280 | 100%
Exterior insect screening of outdoor living spaces |  |  | 3000 | 300 | 3300 | 0.7231% | 0% | 0 | 0 | 0 | 3300 | 100%
DIVISION 11 EQUIPMENT (kitchen)
Appliances: appliance purchase (if any, by GC) |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | #DIV/0!
Appliances: unload, move, installation by GC |  |  | 1500 | 150 | 1650 | 0.3616% | 0% | 0 | 0 | 0 | 1650 | 100%
DIVISION 12 FURNISHINGS
Window treatments (if any by GC) |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | #DIV/0!
DIVISION 13 SPECIAL CONSTRUCTION (pools, other)
Pool, Sauna, Spa |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | #DIV/0!
DIVISION 14 CONVEYING SYSTEMS (elevators)
Elevator (Shaft, when not part of above) |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | #DIV/0!
Elevator (Unit purchase, delivery, install & test) |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | #DIV/0!
DIVISION 15 H (HVAC)
HVAC: Rough-in, ducts (does not include units), wall caps |  |  | 3500 | 350 | 3850 | 0.8436% | 0% | 0 | 0 | 0 | 3850 | 100%
Exhaust ducts & fans, range hood exhaust, dampers |  |  | 2500 | 250 | 2750 | 0.6026% | 0% | 0 | 0 | 0 | 2750 | 100%
Testing of ductwork air-tightness |  |  | 850 | 85 | 935 | 0.2049% | 0% | 0 | 0 | 0 | 935 | 100%
HVAC Exterior Compressor(s) &/or Heat Pump(s) install |  |  | 3500 | 350 | 3850 | 0.8436% | 0% | 0 | 0 | 0 | 3850 | 100%
Interior AHU (Air Handling Unit(s) & Furnace Units (if any)) |  |  | 2000 | 200 | 2200 | 0.4821% | 0% | 0 | 0 | 0 | 2200 | 100%
also interior Trimout for HVAC, balancing
DIVISION 15 P (Plumbing)
Plumbing: Rough-in (includes tub/shower inserts) |  |  | 3500 | 350 | 3850 | 0.8436% | 0% | 0 | 0 | 0 | 3850 | 100%
Plumbing: Trim-out: Fixtures (includes toilets, water heater(s)) |  |  | 4000 | 400 | 4400 | 0.9642% | 0% | 0 | 0 | 0 | 4400 | 100%
Plumbing: Gas System |  |  | 2700 | 270 | 2970 | 0.6508% | 0% | 0 | 0 | 0 | 2970 | 100%
Plumbing: Fire Sprinkler (if any) |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | #DIV/0!
DIVISION 16 ELECTRICAL (includes smoke and CO detection)
Electrical: Rough-in |  |  | 4500 | 450 | 4950 | 1.085% | 0% | 0 | 0 | 0 | 4950 | 100%
Electrical: Trim-out: Fixtures (including switches, outlets) |  |  | 4800 | 480 | 5280 | 1.157% | 0% | 0 | 0 | 0 | 5280 | 100%
DIVISION 17 LOW VOLTAGE SYSTEMS
Systems: Rough-in (low voltage) |  |  | 3600 | 360 | 3960 | 0.8677% | 0% | 0 | 0 | 0 | 3960 | 100%
Systems: Trim-out (low voltage) |  |  | 1900 | 190 | 2090 | 0.458% | 0% | 0 | 0 | 0 | 2090 | 100%
CUSTOM ITEMS
Custom item |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | #DIV/0!
Custom item |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | #DIV/0!
Custom item |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | #DIV/0!
Sub-Total Cost |  | (not including GC profit) | 414870
Total Percent | [5 empty] | 100%
Earned to date-----------------------------------------------------------------------------------------------------------------------------------------------------> | [7 empty] | 0
% complete to date:-----------------------------------------------------------------------------------------------------------------------------> | [6 empty] | 0%
Previous amount billed to date:--------------------------------------------------------------------------------------------------------------------------------------------------> | [8 empty] | 0
Amount earned for this Pay Request:-------------------------------------------------------------------------------------------------------------------------------------------------------------> | [9 empty] | 0
Amount remaning to complete: -----------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------> | [10 empty] | 456357
Amount % remaining to complete: ------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------> | [11 empty] | 100%
Retainage ACCUMULATED per agreement between Contractor and Owner (to date):--------------------------------------------------> | [7 empty] | 0
Retainage per agreement between Contractor and Owner (DEDUCTED FROM THIS NEW PAY REQUEST):---------------------------------------------------------> | [9 empty] | 0 | <--Amount Owner is to deposit into retainage account until Final Payment to GC
Amount Earned this Pay Request minus retainage:------------------------------------------------------------------------------------------------------------------------------------------> | [9 empty] | 0 | <--NOW DUE & PAYABLE
Total Cost to Construct |  |  | 456357 |  | 456357
(includes profit below)
Builder related items:
Supervision |  | (see line item 1 above)
Profit |  |  | 41487 | 41487
Profit %: | (GC enter profit % while Bidding here then leave fixed)-----> |  | 10%
Retainage % (if any) per Contract between GC & Owner: --------------------------------> |  |  |  | 5%
Note regarding possible overall State tax on total:
Rarely, a state may require an overall State tax on top of the total amount (including profit).
To date, only the State of Washington has been discovered to have this policy. If you are a GC bidding this project and you are aware that the State of this project Does have such a tax, immediately notify the Architect so that this form can be adjusted to accommmodate this.
This form is intended for these 4 integrated uses by the General Contractor
TM