## Sheet1
[5 empty] | ArCHchart 2016.4 | ArCHchart™
Updated: | 2016-05-25 |  | PURPOSE OF THIS CHART | WHY
|  |  | To help Clients understand: | To help Clients feel more
|  |  | A. The Architectural Project Process | comfortable with the
|  |  | B. To see "What's Next?" | project process, allowing
|  |  | C. Client role in the project | them to relax & enjoy it,
|  |  | D. Where the project is right now | reducing stress, being
able to plan.
SITE WALK/SITE ANALYSIS |  | SITE WALK/SITE ANALYSIS | INSTRUCTIONS FOR ARCHITECTS | This chart is Not intended to
Client Review |  | Client Review | USING THIS APPLICATION: | be a schedule, nor is it
PROGRAMMING |  | PROGRAMMING |  | intended to have any
|  |  | 1. ERASE THESE RED INSTRUCTIONS | precision. It depicts
Client Review |  |  | BEFORE SENDING THIS TO ANY | sequencing and relative
SCHEMATIC DESIGN |  | Client Review | CLIENT. | proportions of time in each
Floor Plans |  |  |  | phase with respect to other
Site Plan |  |  | 2. MAKE SURE YOU READ | phases.
Client requested changes |  | SCHEMATIC DESIGN | EVERYTHING ON THIS
Client Review |  | Floor Plans | APPLICATION, INCLUDING THE | NOTES
DESIGN DEVELOPMENT |  | Site Plan | NOTES TO THE RIGHT, SO THAT YOU | Note 1: CLIENT REVIEW TIME
Front Elevation |  |  | UNDERSTAND THE TERMS AND | Typical Progress Chart depicts
Additional Elevations |  | Client requested | LIMITATIONS OF THIS | Client review time as minimal
Floor Plans: more info. |  | changes | APPLICATION. | after each phase. Clients can
Site Plan: coordination |  |  |  | sometimes take a week to over a
Client Geotechnical Engineer |  | Client Review | 3. YOU MAY ADJUST THIS BAR | month or more to respond to
Client requested changes |  |  | CHART, INCLUDING THE ITEMS AS | submittals sent to them from the
Client Review |  |  | YOU WISH TO SUIT YOUR PROCESS | Architect. Architect therefore has
CONSTRUCTION |  | DESIGN DEVELOPMENT | AND EACH PROJECT. IT IS | no control over Client review
DOCUMENTS |  | Front Elevation | PURPOSELY SIMPLE AND WITHOUT | time(s). This means: extended
Floor Plans |  | Additional Elevations | THE USUAL FORMULAS YOU | Client review times can
Elevations |  | Floor Plans: more info. | TYPICALLY MIGHT SEE IN AN EXCEL | significantly extend overall
Roof Plan(s) |  | Site Plan: coordination | APPLICATION. IN OTHER WORDS, | project time.
Site Plan |  | Client Geotechnical Engineer | IF YOU WANT TO TURN THIS INTO A | Note 2: CLIENT CHANGES
Notes/key notes |  |  | HARD CORE SCHEDULE WITH WEEKS | Client requested changes to
Building Section(s) |  | Client requested | FOR EACH ROW (OR DAYS), GO | design & documents can and will
Wall Sections |  | changes | RIGHT AHEAD. JUST BE CAREFUL | extend each phase in which they
Details |  |  | WHAT MONSTER YOU CREATE FOR | occur and also extend the overall
Door & Finish Schedules |  | Client Review | YOURSELF TO MANAGE. | project schedule through no fault
General info sheets |  |  |  | of the Architect's.
Client Structural Engineer |  |  | 4. WE SUGGEST THAT YOU NOT | Note 3: DIAGRAMMATIC CHART
(not by Architect) |  | CONSTRUCTION | TURN THIS INTO A REAL | Bar charts on this sheet are not
Specifications |  | DOCUMENTS | SCHEDULE. WHY: YOUR CLIENTS | meant to accurately depict
Coordination |  | Floor Plans | MAY START TO TRY TO MANAGE | precise numbers of days, weeks
Client requested changes |  | Elevations | YOU AND CRITICIZE YOU IF YOU | or months. Rather, they show
Client Review |  | Roof Plan(s) | ARE NOT "ON TRACK." | general relative proportions. For
BIDDING |  | Site Plan |  | instance: Construction Documents
(obtain pricing usually |  | Notes/key notes |  | takes longer than other
more than Client wishes |  | Building Section(s) |  | architectural project phases,
to pay to build project) |  | Wall Sections |  | except for Construction
Client should expect this & |  | Details |  | Administration.
plan for cost overages. |  | Door & Finish Schedules |  | Note 4: NOT ALL-INCLUSIVE
Client Review |  | General info sheets |  | These are primarily Architectural
CLIENT START FINANCING |  | Client Structural Engineer |  | project phases & tasks. Meaning:
Client fill out loan forms |  | (not by Architect) |  | discliplines and trades outside of
VALUE ENGINEERING |  | Specifications | 5. CLICK ON THE OUTER EDGE OF | Architectural services are not
Architect negotiate with GC |  | Coordination | THIS "YOU ARE HERE" ARROW AND | necessarily accounted for in this
to reduce pricing |  | Other | PRESS YOUR SHIFT KEY THEN DRAG | chart (such as but not limited to
Client Review |  | Client requested | ARROW UP OR DOWN, TO ALIGN | Structural Engineering), which can
CLIENT FINANCING |  | changes | WITH THE CURRENT PROJECT | impact this project length.
Underwriting review |  |  | PROGRESS. | Note 5: SCOPE OF WORK
GENERAL CONTRACTOR- |  | Client Review |  | The Professional Services choices
CLIENT AGREEMENT |  |  | 6. ADD. MODIFY OR DELETE ROWS & | you made when signing your
CLIENT FINANCING |  |  | ITEMS FROM THE PROJECT CHART | agreement with your Architect
Finalization |  | BIDDING | ACTIVITIES AS YOU DEEM | impact the Architect's activities.
GC-Owner Contract SIGN |  | (obtain pricing usually | APPROPRIATE FOR YOUR COMPANY | So: the activities you see in the
CONTRACTOR |  | more than Client wishes | PROCESS. BE CAREFUL NOT TO | charts on this particular form may
MOBILIZATION |  | to pay to build project) | DELETE THE DARK GRAY NOTES TO | be more or less than what you
|  | Client should expect this & | THE RIGHT WHEN YOU DO THAT. | will receive from your Architect.
|  | plan for cost overages. |  | This chart is Not your agreement.
CONSTRUCTION |  | Client Review | 7. IT IS RECOMMENDED THAT YOU | The Architect is not obligated to
ADMINISTRATION |  | CLIENT START FINANCING | NEVER SEND THIS FILE AS A REAL | perform more services than you
|  | Client fill out loan forms | EXCEL FILE TO YOUR CLIENTS. THEY | selected in your agreement with
|  | VALUE ENGINEERING | MIGHT CHANGE SOMETHING AND | them. You may not receive all of
|  | Architect negotiate with GC | THEN IMAGINE YOU HAD THAT IN | the services indicated in this chart,
|  | to reduce pricing | THE DIAGRAM AND THEN YOU | unless you selected those in the
|  | Client Review | COULD BE BLAMED FOR THE | agreement. Consult your
|  | CLIENT FINANCING | CHANGE. SAME REASON YOU | agreement.
|  | Underwriting review | PROBABLY DON'T WANT TO SEND | Note 6: PAYMENT DELAYS
|  | GENERAL CONTRACTOR- | THEM A REAL REVIT OR AUTOCAD | Delays in payment to the
|  | CLIENT AGREEMENT | FILE. IT IS SUGGESTED THAT YOU | Architect can cause delays in the
|  | CLIENT FINANCING | ALWAYS SEND YOUR CLIENTS A PDF | Architect's work schedule. Prompt
|  | Finalization | FILE THAT THEY CANNOT CHANGE. | payment helps sustain project
|  | GC-Owner Contract SIGN | THAT WAY IT IS FROZEN UNTIL | inertia.
|  | CONTRACTOR | YOU CHANGE IT AND SEND THEM | Note 7: CLIENT FINANCING
|  | MOBILIZATION | A NEW PDF. | Client's financing can take more
time to obtain than Client
|  |  | 8. ANOTHER METHOD OF | anticipates, which can add
|  | CONSTRUCTION | PRESENTATION IS TO PUT THIS | considerably to the time required
|  | ADMINISTRATION | CHART ONTO A PROJECT WEBPAGE | to go through this project process,
|  |  | FOR YOUR CLIENTS ON YOUR | which has nothing to do with the
|  | Pay Requests: | WEBSITE AND PROVIDE A | Architect or Contractor. Your
|  | Highly recommended that | PASSWORD FOR THAT PAGE SO | lender's performance determines
|  | Architect review General | THAT CLIENT INFORMATION IS | the time added to your project
|  | Contractor (GC) Pay | SECURE. YOU COULD THEN | process for securing your
|  | Requests prior to Owner | PROVIDE A LINK TO A JPG OR PDF | financing. This may not apply to
|  | paying them. | IN YOUR WEBSITE LIBRARY OF | you, if you are paying cash for
|  |  | MEDIA THAT YOUR CLIENT COULD | your project construction.
|  | Submittals/Shop Drawings: | CLICK TO DOWNLOAD AND SEE. | Note 8: CA ACTIVITIES
|  | Recommend Architect | YOU COULD THEN UPDATE THIS | A Construction Administration (CA)
|  | review GC product | CHART ONCE A WEEK, PERHAPS, | list of services to be provided by
|  | submittals & shop drawings | OR AS YOUR PROJECT REQUIRED. | your Architect will be sent to you
|  | for items to go into project. |  | in an email from your Architect,
|  | It is quite common for | 9. BEWARE THAT THIS CHART | describing which CA activities
|  | GCs to take liberties or | DOESN'T RESULT IN YOUR FIRM | your Architect will be performing
|  | make changes without | BEING RELIEVED OF DUTIES BEFORE | on your behalf, IF you selected
|  | notifying Owner during | YOU ARE DONE WITH THE PROJECT, | CA as part of your Architect's
|  | construction, usually | IF YOU BELIEVE THAT A PARTICULAR | services in your agreement with
|  | without Owner's | CLIENT MIGHT REACT NEGATIVELY | your Architect. You will NOT
|  | knowledge = cheapening | TO PROGRESS INFORMATION LIKE | receive any CA services from
|  | of construction quality = | THIS AND LET YOU GO BECAUSE | your Architect if you did not
|  | lower durability = | THEY DON'T RECALL HOW MUCH | select CA services in your
|  | more repairs and more | THEY MIGHT ULTIMATELY PAY YOU, | agreement with your Architect.
|  | costly during home | THEN SEE INADEQUATE PROGRESS | These services are highly
|  | ownership (unless Architect | IN THEIR MINDS AND STOP THE JOB | detailed and time-intensive and
|  | has opportunity to catch | BECAUSE THEY JUDGE THE | are not provided gratuitously. In
|  | these unauthorized | REMAINDER OF YOUR WORK WILL | other words, the activities seen in
|  | substitutions). | COST TOO MUCH. YOU SHOULD | the diagrammic bar chart to the
|  |  | HAVE A CLEAR UNDERSTANDING | left may or may not be included
|  | Site Visits: | WITH YOUR CLIENTS FOR WHOM | in the services provided to you
|  | Recommend Architect make | YOU PROVIDE THIS CHART AS TO | by your Architect, per the choices
SUBSTANTIAL |  | periodic site visits during | HOW YOU CHARGE FOR YOUR | you made in your agreement
COMPLETION |  | construction to compare | SERVICES AND AT LEAST WHAT THE | with your Architect, and per the
|  | with approved CDs | TOTAL MIGHT AMOUNT TO SO | list your Architect may have or
|  | (Construction Documents). | NEGATIVE THINGS DO NOT OCCUR. | will send you describing what
services he will be providing you.
FINAL COMPLETION |  | Coordination: | 10. THIS CHART HAS NO LINKS TO
|  | With your Bank. | YOUR BILLINGS. HOWEVER, IF YOU
INITIAL UMBRELLA |  | With your Insurance | BELIEVE THAT PROVIDING AN
WARRANTEE PERIOD |  | company. | UPDATE OF THIS WITH YOUR
|  | With the GC. | INVOICES MIGHT HELP YOUR
|  | With your HOA (Home | CLIENTS TO UNDERSTAND "WHAT'S
|  | Owner's Association). | NEXT", YOU CAN DO SO.
|  | With the Building | SEE ITEM 9.
Department.
|  | And others. | 11. BEWARE OF SENDING TOO
MANY UPDATES OF THIS CHART TO
|  | Day to day: | YOUR CLIENTS. IT MIGHT APPEAR
|  | coordination with your GC. | THAT YOUR PROGRESS IS TOO
|  | Other tasks. | SMALL. YOU MAY SIMPLY WANT TO
|  | POSSIBLE CLIENT LOAN | USE THE METHOD IN ITEM 8. THAT
|  | CONSTRUCTION | DOESN'T CALL UNDUE ATTENTION
|  | EXTENSION | TO THE PROJECT PROGRESS,
|  | (can happen) | HOWEVER, IT ALLOWS CLIENTS TO
CHECK THAT WHENEVER THEY
WISH.
YOU MAY WANT TO START THE
PROJECT WITH AN EXPLANATION
|  | SUBSTANTIAL | OF THIS CHART TO HELP ORIENT
|  | COMPLETION | YOUR CLIENTS AND TO HELP THEM
UNDERSTAND "WHAT'S NEXT."
RECOMMEND ELECTRONIC LINKS
FOR FUTURE UPDATES.
FINAL COMPLETION
12. ONCE AGAIN:
|  | INITIAL UMBRELLA | DELETE THESE RED INSTRUCTIONS
|  | WARRANTEE PERIOD | BEFORE SENDING TO CLIENTS
13. IT IS SUGGESTED THAT YOU
KEEP THIS VERTICAL FORMAT.
WHY: YOU CAN READ THIS
APPLICATION ON A SMART PHONE
IF YOU TURN IT SIDEWAYS AND
SCROLL DOWN. YOU DO NOT WANT
TO LOSE THAT FUNCTIONALITY, AS
CLIENTS ARE USING PHONE APPS
MORE AND MORE EACH DAY AND
YOU WANT TO BE CONVENIENT
FOR THEM.
14. INITIALLY, EACH ROW
(BETWEEN THE 2 BAR CHARTS) WAS
INTENDED TO REPRESENT A WEEK,
Optional |  |  | BUT THAT COULD ALSO REPRESENT
Architect Warrantee |  |  | A DAY, OR SIMPLY THE PASSAGE OF
Site Visit/Report |  |  | TIME. IT IS SUGGESTED THAT YOU
Contractor warrantee |  |  | SIMPLY LET THE ROWS = PASSAGE
repairs |  |  | OF TIME. OTHERWISE, IT WILL
COME BACK TO HAUNT YOU IF YOU
VARY FROM A CLIENT
POST WARRANTEE |  |  | EXPECTATION.
PERIOD
Optional
Architect Warrantee
Site Visit/Report
Contractor warrantee
repairs
POST WARRANTEE
PERIOD
Project
Start
YOU ARE HERE
items below this point can & will change
time
Project
Start
ArCHchart © Copyright 2016,
ArCH: Architects Creating Homes, LLC
All Rights Reserved Worldwide.
Project Chart
CURRENT PROJECT
PROGRESS &
PROJECTED CHART
TYPICAL
CHART