## Sheet1
[5 empty] | ArCHchart 2016.3 | ArCHchart™
Updated: | 2016-05-11 |  | PURPOSE OF THIS CHART | WHY
|  |  | To help Clients understand: | To help Clients feel more
|  |  | A. The Architectural Project Process | comfortable with the
|  |  | B. To see "What's Next?" | project process, allowing
|  |  | C. Client role in the project | them to relax & enjoy it,
|  |  | D. Where the project is right now | reducing stress, being
able to plan.
SITE WALK/SITE ANALYSIS |  | (no site walk) | INSTRUCTIONS FOR ARCHITECTS | This chart is Not intended to
Client Review |  | Remote site analysis | USING THIS APPLICATION: | be a schedule, nor is it
PROGRAMMING |  | PROGRAMMING |  | intended to have any
|  |  | 1. ERASE THESE RED INSTRUCTIONS | precision. It depicts
Client Review |  |  | BEFORE SENDING THIS TO ANY | sequencing and relative
SCHEMATIC DESIGN |  | Client Review | CLIENT. | proportions of time in each
Floor Plans |  |  |  | phase with respect to other
Site Plan |  |  | 2. MAKE SURE YOU READ | phases.
|  | SCHEMATIC DESIGN | EVERYTHING ON THIS
Client Review |  | Floor Plans | APPLICATION, INCLUDING THE
DESIGN DEVELOPMENT |  | Site Plan | NOTES TO THE RIGHT, SO THAT YOU | NOTES
Front Elevation |  |  | UNDERSTAND THE TERMS AND | Note 1: CLIENT REVIEW TIME
Additional Elevations |  | Client requested | LIMITATIONS OF THIS | Typical Progress Chart depicts
Floor Plans: more info. |  | changes | APPLICATION. | Client review time as minimal
Site Plan: coordination |  |  |  | after each phase. Clients can
|  | Client Review | 3. YOU MAY ADJUST THIS | sometimes take a week to over a
Client Review |  |  | APPLICATION AS YOU WISH TO SUIT | month or more to respond to
CONSTRUCTION |  |  | YOUR PRACTICE AND EACH | submittals sent to them from the
DOCUMENTS |  | DESIGN DEVELOPMENT | PROJECT. IT IS PURPOSELY SIMPLE | Architect. Architect therefore has
Floor Plans |  | Front Elevation | AND WITHOUT THE USUAL | no control over Client review
Elevations |  | Additional Elevations | FORMULAS YOU TYPICALLY MIGHT | time(s). This means: extended
Roof Plan(s) |  | Floor Plans: more info. | SEE IN AN EXCEL APPLICATION. IN | Client review times can
Site Plan |  | Site Plan: coordination | OTHER WORDS, IF YOU WANT TO | significantly extend overall
Notes/key notes |  |  | TURN THIS INTO A HARD CORE | project time.
Building Section(s) |  | Client requested | SCHEDULE WITH WEEKS FOR EACH | Note 2: CLIENT CHANGES
Wall Sections |  | changes | ROW (OR DAYS), GO RIGHT AHEAD. | Client requested changes to
Details |  |  | JUST BE CAREFUL WHAT MONSTER | design & documents can and will
Door & Finish Schedules |  | Client Review | YOU CREATE FOR YOURSELF TO | extend each phase in which they
General info sheets |  |  | MANAGE. | occur and also extend the overall
Client Structural Engineer |  |  |  | project schedule through no fault
(not by Architect) |  | CONSTRUCTION | 4. WE SUGGEST THAT YOU NOT | of the Architect's.
Specifications |  | DOCUMENTS | TURN THIS INTO A REAL | Note 3: DIAGRAMMATIC CHART
Coordination |  | Floor Plans | SCHEDULE. WHY: YOUR CLIENTS | Bar charts on this sheet are not
Client Review |  | Elevations | MAY START TO TRY TO MANAGE | meant to accurately depict
BIDDING |  | Roof Plan(s) | YOU AND CRITICIZE YOU IF YOU | precise numbers of days, weeks
(obtain pricing usually |  | Site Plan | ARE NOT "ON TRACK." | or months. Rather, they show
more than Client wishes |  | Notes/key notes |  | general relative proportions. For
to pay to build project) |  | Building Section(s) |  | instance: Construction Documents
Client should expect this & |  | Wall Sections |  | takes longer than other
plan for cost overages. |  | Details |  | architectural project phases,
Client Review |  | Door & Finish Schedules |  | except for Construction
CLIENT START FINANCING |  | General info sheets |  | Administration.
Client fill out loan forms |  | Client Structural Engineer | 5. CLICK ON THE OUTER EDGE OF | Note 4: NOT ALL-INCLUSIVE
VALUE ENGINEERING |  | (not by Architect) | THIS "YOU ARE HERE" ARROW AND | These are primarily Architectural
Architect negotiate with GC |  | Specifications | PRESS YOUR SHIFT KEY THEN DRAG | project phases & tasks. Meaning:
to reduce pricing |  | Coordination | ARROW UP OR DOWN, TO ALIGN | discliplines and trades outside of
Client Review |  | Other | WITH THE CURRENT PROJECT | Architectural services are not
CLIENT FINANCING |  | Client requested | PROGRESS. | necessarily accounted for in this
Underwriting review |  | changes |  | chart (such as but not limited to
GENERAL CONTRACTOR- |  |  | 6. ADD OR DELETE ROWS AND | Structural Engineering), which can
CLIENT AGREEMENT |  | Client Review | ITEMS FROM THE PROJECT CHART | impact this project length.
CLIENT FINANCING |  |  | ACTIVITIES AS YOU DEEM | Note 5: SCOPE OF WORK
Finalization |  |  | APPROPRIATE FOR YOUR COMPANY | The Professional Services choices
GC-Owner Contract SIGN |  | BIDDING | PROCESS. BE CAREFUL NOT TO | you made when signing your
CONTRACTOR |  | (obtain pricing usually | DELETE THE DARK GRAY NOTES TO | agreement with your Architect
MOBILIZATION |  | more than Client wishes | THE RIGHT WHEN YOU DO THAT. | impact the Architect's activities.
|  | to pay to build project) |  | So: the activities you see in the
|  | Client should expect this & | 7. IT IS RECOMMENDED THAT YOU | charts on this particular form may
CONSTRUCTION |  | plan for cost overages. | NEVER SEND THIS FILE AS A REAL | be more or less than what you
ADMINISTRATION |  | Client Review | EXCEL FILE TO YOUR CLIENTS. THEY | will receive from your Architect.
|  | CLIENT START FINANCING | MIGHT CHANGE SOMETHING AND | This chart is Not your agreement.
|  | Client fill out loan forms | THEN IMAGINE YOU HAD THAT IN | The Architect is not obligated to
|  | VALUE ENGINEERING | THE DIAGRAM AND THEN YOU | perform more services than you
|  | Architect negotiate with GC | COULD BE BLAMED FOR THE | selected in your agreement with
|  | to reduce pricing | CHANGE. SAME REASON YOU | them. You may not receive all of
|  | Client Review | PROBABLY DON'T WANT TO SEND | the services indicated in this chart,
|  | CLIENT FINANCING | THEM A REAL REVIT OR AUTOCAD | unless you selected those in the
|  | Underwriting review | FILE. IT IS SUGGESTED THAT YOU | agreement. Consult your
|  | GENERAL CONTRACTOR- | ALWAYS SEND YOUR CLIENTS A PDF | agreement.
|  | CLIENT AGREEMENT | FILE THAT THEY CANNOT CHANGE. | Note 6: PAYMENT DELAYS
|  | CLIENT FINANCING | THAT WAY IT IS FROZEN UNTIL | Delays in payment to the
|  | Finalization | YOU CHANGE IT AND SEND THEM | Architect can cause delays in the
|  | GC-Owner Contract SIGN | A NEW PDF. | Architect's work schedule. Prompt
|  | CONTRACTOR |  | payment helps sustain project
|  | MOBILIZATION | 8. ANOTHER METHOD OF | inertia.
|  |  | PRESENTATION IS TO PUT THIS | Note 7: CLIENT FINANCING
|  |  | CHART ONTO A PROJECT WEBPAGE | Client's financing can take more
|  | CONSTRUCTION | FOR YOUR CLIENTS ON YOUR | time to obtain than Client
|  | ADMINISTRATION | WEBSITE AND PROVIDE A | anticipates, which can add
|  |  | PASSWORD FOR THAT PAGE SO | considerably to the time required
|  | Pay Requests: | THAT CLIENT INFORMATION IS | to go through this project process,
|  | Highly recommended that | SECURE. YOU COULD THEN | which has nothing to do with the
|  | Architect review General | PROVIDE A LINK TO A JPG OR PDF | Architect or Contractor. Your
|  | Contractor (GC) Pay | IN YOUR WEBSITE LIBRARY OF | lender's performance determines
|  | Requests prior to Owner | MEDIA THAT YOUR CLIENT COULD | the time added to your project
|  | paying them. | CLICK TO DOWNLOAD AND SEE. | process for securing your
|  |  | YOU COULD THEN UPDATE THIS | financing. This may not apply to
|  | Submittals/Shop Drawings: | CHART ONCE A WEEK, PERHAPS, | you, if you are paying cash for
|  | Recommend Architect | OR AS YOUR PROJECT REQUIRED. | your project construction.
|  | review GC product |  | Note 8: CA ACTIVITIES
|  | submittals & shop drawings | 9. BEWARE THAT THIS CHART | A Construction Administration (CA)
|  | for items to go into project. | DOESN'T RESULT IN YOUR FIRM | list of services to be provided by
|  | It is quite common for | BEING RELIEVED OF DUTIES BEFORE | your Architect will be sent to you
|  | GCs to take liberties or | YOU ARE DONE WITH THE PROJECT, | in an email from your Architect,
|  | make changes without | IF YOU BELIEVE THAT A PARTICULAR | describing which CA activities
|  | notifying Owner during | CLIENT MIGHT REACT NEGATIVELY | your Architect will be performing
|  | construction, usually | TO PROGRESS INFORMATION LIKE | on your behalf, IF you selected
|  | without Owner's | THIS AND LET YOU GO BECAUSE | CA as part of your Architect's
|  | knowledge = cheapening | THEY DON'T RECALL HOW MUCH | services in your agreement with
|  | of construction quality = | THEY MIGHT ULTIMATELY PAY YOU, | your Architect. You will NOT
|  | lower durability = | THEN SEE INADEQUATE PROGRESS | receive any CA services from
|  | more repairs and more | IN THEIR MINDS AND STOP THE JOB | your Architect if you did not
|  | costly during home | BECAUSE THEY JUDGE THE | select CA services in your
|  | ownership (unless Architect | REMAINDER OF YOUR WORK WILL | agreement with your Architect.
|  | has opportunity to catch | COST TOO MUCH. YOU SHOULD | These services are highly
|  | these unauthorized | HAVE A CLEAR UNDERSTANDING | detailed and time-intensive and
|  | substitutions). | WITH YOUR CLIENTS FOR WHOM | are not provided gratuitously. In
|  |  | YOU PROVIDE THIS CHART AS TO | other words, the activities seen in
|  | Site Visits: | HOW YOU CHARGE FOR YOUR | the diagrammic bar chart to the
SUBSTANTIAL |  | Recommend Architect make | SERVICES AND AT LEAST WHAT THE | left may or may not be included
COMPLETION |  | periodic site visits during | TOTAL MIGHT AMOUNT TO SO | in the services provided to you
|  | construction to compare | NEGATIVE THINGS DO NOT OCCUR. | by your Architect, per the choices
|  | with approved CDs |  | you made in your agreement
|  | (Construction Documents). | 10. THIS CHART HAS NO LINKS TO | with your Architect, and per the
FINAL COMPLETION |  |  | YOUR BILLINGS. HOWEVER, IF YOU | list your Architect may have or
|  | Coordination: | BELIEVE THAT PROVIDING AN | will send you describing what
INITIAL UMBRELLA |  | With your Bank. | UPDATE OF THIS WITH YOUR | services he will be providing you.
WARRANTEE PERIOD |  | With your Insurance | INVOICES MIGHT HELP YOUR
|  | company. | CLIENTS TO UNDERSTAND "WHAT'S
|  | With the GC. | NEXT", YOU CAN DO SO.
|  | With your HOA (Home | SEE ITEM 9.
Owner's Association).
|  | With the Building | 11. BEWARE OF SENDING TOO
|  | Department. | MANY UPDATES OF THIS CHART TO
|  | And others. | YOUR CLIENTS. IT MIGHT APPEAR
THAT YOUR PROGRESS IS TOO
|  | Day to day: | SMALL. YOU MAY SIMPLY WANT TO
|  | coordination with your GC. | USE THE METHOD IN ITEM 8. THAT
|  | Other tasks. | DOESN'T CALL UNDUE ATTENTION
|  | POSSIBLE CLIENT LOAN | TO THE PROJECT PROGRESS,
|  | CONSTRUCTION | HOWEVER, IT ALLOWS CLIENTS TO
|  | EXTENSION | CHECK THAT WHENEVER THEY
|  | (can happen) | WISH.
YOU MAY WANT TO START THE
PROJECT WITH AN EXPLANATION
OF THIS CHART TO HELP ORIENT
YOUR CLIENTS AND TO HELP THEM
|  | SUBSTANTIAL | UNDERSTAND "WHAT'S NEXT."
|  | COMPLETION | RECOMMEND ELECTRONIC LINKS
FOR FUTURE UPDATES.
12. ONCE AGAIN:
|  | FINAL COMPLETION | DELETE THESE RED INSTRUCTIONS
BEFORE SENDING TO CLIENTS
INITIAL UMBRELLA
|  | WARRANTEE PERIOD | 13. IT IS SUGGESTED THAT YOU
KEEP THIS VERTICAL FORMAT.
WHY: YOU CAN READ THIS
APPLICATION ON A SMART PHONE
IF YOU TURN IT SIDEWAYS AND
SCROLL DOWN. YOU DO NOT WANT
TO LOSE THAT FUNCTIONALITY, AS
CLIENTS ARE USING PHONE APPS
MORE AND MORE EACH DAY AND
YOU WANT TO BE CONVENIENT
FOR THEM.
14. INITIALLY, EACH ROW
(BETWEEN THE 2 BAR CHARTS) WAS
INTENDED TO REPRESENT A WEEK,
BUT THAT COULD ALSO REPRESENT
Optional |  |  | A DAY, OR SIMPLY THE PASSAGE OF
Architect Warrantee |  |  | TIME. IT IS SUGGESTED THAT YOU
Site Visit/Report |  |  | SIMPLY LET THE ROWS = PASSAGE
Contractor warrantee |  |  | OF TIME. OTHERWISE, IT WILL
repairs |  |  | COME BACK TO HAUNT YOU IF YOU
VARY FROM A CLIENT
EXPECTATION.
POST WARRANTEE
PERIOD
Optional
Architect Warrantee
Site Visit/Report
Contractor warrantee
repairs
POST WARRANTEE
PERIOD
Project
Start
YOU ARE HERE
items below this point can & will change
time
Project
Start
ArCHchart © Copyright 2016,
ArCH: Architects Creating Homes, LLC
All Rights Reserved Worldwide.
Project Chart
CURRENT PROJECT
PROGRESS &
PROJECTED CHART
TYPICAL
CHART